Items in blue relate to oddshocks’ charsheet project.
###### Week 1 (June 4th - 8th)
- June 4th: Initialized blogs, learned IRC, and created accounts on github.
- June 4th: Started Preliminary Research document to store all rough drafts, charts, and summaries for individual papers
- June 5th: Started Research Essays document
- June 5th: Started User Generated Content Info document for research into User Generated Content
- June 5th: Completed User Generated Content Info document
- June 7th: Completed Preliminary Research document
- June 8th: Compiled papers into a Fedora RPG: Preliminary Research document
###### Week 2 (June 11th - 15th)
- June 11th: Researched real money trading, geosocial services, etc
- June 11th: Playtested MMORPG and social games
- June 11th: Investigated open source tech and completed a general analyses survey for each
- June 12th: Started Research Outlines document to summarize our results for the initial questions from SJ
- June 12th: Completed Research Outlines document
- June 13th: Started Game Analysis Matrix spreadsheet to store all game analyses in an easy to view matrix
- June 14th: Completed Game Analysis Matrix spreadsheet
- June 14th: Started Open Source Tech Matrix spreadsheet to store all open technology info in an easy to view matrix
- June 14th: Started Open Source Tech Analysis document to store all open technology analyses in an easy to view matrix
###### Week 3 (June 18th - 22nd)
- June 18th: Started RPG and Social Game Mechanics spreadsheet to store all game mechanic information in an easy to view matrix
- June 18th: Completed Game Analyses document
- June 18th: Completed Open Source Tech Matrix spreadsheet
- June 19th: Completed RPG and Social Game Mechanics spreadsheet
- June 19th: Started Game Analysis Quicklook spreadsheet to store all Game Analyses information in an easy to view matrix
- June 19th: Completed Game Analysis Quicklook spreadsheet
- June 19th: Completed Open Source Tech Analysis doc
- June 19th: Completed Open Source Tech Quicklook spreadshee
- June 20th: Started Commarch Thoughts on Game Tech document to determine what group members thought of each technology
- June 20th: Completed Commarch Thoughts on Game Tech document
- June 21st: Started Research: 2D RPGs document
- June 21st: Started Plan for 6/21-6/29 spreadsheet
- June 21st: Completed Plan for 6/21-6/29 spreadsheet
- June 21st: Started Contact Vitals document
- June 22nd: Sent up-to-date work to RedHat for review
- June 18th: Playtested various RPGs including Super Mario RPG, FF1, Ocarina of Time, Earthbound, and Secret of Mana
###### Week 4 (June 25th - 29th)
- June 25th: Received feedback from RedHat
- June 25th: Research: 2D RPGs doc completed
- June 25th: Contacted various Open Source collectives and companies
- June 26th: Began designing combat systems, mechanics, and setting
- June 26th: Game experience brainstorming session
- June 26th: Started Brainstorming Game Experience document to hold information from brainstorming session
- June 26th: Discussed MDA (Mechanics, Dynamics, Aesthetics)
- June 27th: Contact Status spreadsheet started
- June 27th: Brainstormed negative elements within games
- June 28th: Contact Status spreadsheet completed
- June 28th: Completed Contact Vitas document
- June 28th: Outreach Responses document started
- June 29th: Outreach Responses document completed
###### Week 5 (July 2nd - 6th)
- July 2nd: Started Game Definitions document
- July 2nd: Completed Game Definitions document
- July 2nd: Begin development of charsheet, develop base of app
- Confirmed story and first version of combat
- July 5th: Started Prototype Ideas document to hold information about our Initial paper prototype
- June 6th: Molded game system with the setting
###### Week 6 (July 9th - 13th)
- July 9th: Started High Concept document
- July 9th: Started Game Treatment document
- July 9th: Pull charsheet data in from various sources, work on base functionality and styling
- July 10th: Started API Master Doc
- July 12th: Discussed choice FOSS elements to integrate and implement
- July 13th: Created basic design and feel of the game in the High Concept Document and Game Treatment Document
- July 13th: Added a backstory to the Game Treatment document to fit with the look and feel of the setting
- July 13th: Completed API Master Doc
- July 13th: Had a Symposium meeting with the other fellows of the program
###### Week 7 (July 16th - 20th)
- July 16th: Started Project Abstract document for the 2012 RIT Ugrad Research Symposium
- July 16th: Added combat paper prototype to the Prototype Ideas document
- July 16th: Discussed ideas surrounding the economy
- July 16th: Read and discussed Game Balance Concepts (All 10 weeks)
- July 16th: Add a bunch of features, error handling, close many tickets
- July 16th: Worked on various systems such as trading, crafting, armor, and combat
- July 18th: Completed Project Abstract document and submitted
- July 18th: Started Presentation Day To Do List document
###### Week 8 (July 23rd - 27th)
- July 23rd: Completed High Concept document
- July 23rd: Completed Game Treatment document
- July 23rd: Balance work on the combat, crafting and materials systems
- July 23rd: Testing combat prototype
- July 23rd: Deployment to OpenShift, add more features, work on integrating more APIs
- July 24th: Started Weapons vs Armor spreadsheet
- July 24th: Completed Weapons vs Armor spreadsheet
- July 25th: Started Languages Spreadsheet
- July 25th: Completed Languages Spreadsheet
- July 25th: Started Developer Character Spreadsheet
- July 26th: Started Playtest Scripts and Surveys document
- July 26th: Coding Rates spreadsheet started
- July 26th: Coding Rates spreadsheet completed
- July 26th: Completed Developer Character Spreadsheet
- July 27th: Started Playtest Flyer and preparations for playtesting
- July 27th: Added FOSS integration numbers and balance to Brainstorming Ideas document
- July 27th: Added stat ratios for Developer Character Sheet document
###### Week 9 (July 30th - August 3rd)
- July 30th: Started Game Systems, a compilation of the various systems we developed
- July 30th: Game Systems doc completed
- July 30th: Playtest flyers posted around campus
- July 30th: Implement attributes and skill values, more improvements and additions
- July 30th: Started PowerPoint presentation we’ll use at the Research Symposium
- July 30th: Started Presentation Outline
- July 31st: Started Timeline of our progress
- July 31st: Started Presentation Script
- August 2nd: Playtest session with other fellows
###### Week 10 (August 6th - 10th)
- August 6th: Started Final FOSSopolis powerpoint
- August 7th: Started Final Redhat FOSSopolis powerpoint
- August 8th: Converted powerpoints to Fedora template powerpoints
- August 9th: Went to Red Hat in Boston to give presentation
- August 11th: Saw Boston
###### Week 11 (August 13th - 17th)
- August 13th: Finalized any documents including adding links, correcting typos, etc
- August 13th: Started the Final To Do List doc
- August 13th: Finished all previous documents
- August 13th: Started and Finished Playtestathon Summary document